Working Group on the Audit of Extractive Industries (WGEI)

Stakeholder engagement strategy 2025 - 2027

Contents

List of Acronyms	2

I.	Introduction	3

II.	Mapping the different stakeholders and stakeholder groups	4

III.	Activity plan for stakeholder engagement and outreach 2020-2022	6

List of Acronyms

| ATAF | African Tax Administration Forum |
| --- | --- |
| CBC | INTOSAI Capacity Building Committee |
| CSO | Civil Society Organization |
| DFID | Department for International Development (United Kingdom) |
| EI | Extractive Industries |
| EITI | Extractive Industries Transparency Initiative |
| EU | European Union |
| GIZ | German Corporation for International Cooperation (GmbH) |
| IDI | INTOSAI Development Initiative |
| IMF | International Monetary Fund |
| INTOSAI | International Organization of Supreme Audit Institutions |
| NGO | Non-Governmental Organization |
| NRGI | Natural Resource Governance Institute |
| PWYP | Publish What You Pay |
| SAI | Supreme Audit Institution |
| UNDP | United Nations Development Programme |
| UNODC | United Nations Office on Drugs and Crime |
| WGEA | Working Group on Environmental Audit |
| WGEI | Working Group on Audit of Extractive Industries |

- Introduction

WGEI’s role in engaging key stakeholders

WGEI aims to promote knowledge sharing and networking to enhance SAIs’ capacity in the audit of extractive industries, thereby contributing to good governance and sustainable development in the extractive industries. Since the knowledge is not only to be found among SAIs but also in the larger EI community, having arenas of knowledge sharing and networking which involve various stakeholders is crucial. WGEI has therefore included it as a priority in its activity plan to engage stakeholders.

Before engaging key stakeholders, we first need to map who the relevant stakeholders are in the international EI sector and community. The next step is then to identify ways on how to network and connect with the various stakeholders. Engaging stakeholders is important because many actors/stakeholders in the EI community share common goals, which include ensuring good governance and sustainable development in a way that resource profits will benefit the people of the country and the generations to come.

Engaging stakeholders as a part of the WGEI Activity Plan

WGEI has developed a 3-year Activity Plan for 2023 - 2025 defining specific activities to be undertaken to achieve its goals and objectives. Activity 4 in the Activity Plan deals with networking with key external stakeholders and includes the following specific activities and output:

- Cooperate with INTOSAI regions

- Engate INTOSAI bodies

- Key External stakeholder networking and outreach

d.	Engage academia and research organisations in WGEI activities

Each region will have a focal point SAI which has the responsibility to follow-up on the stakeholder engagement that is specific for the region. The regional focal points will share and coordinate during the annual steering committee meetings as well as during periodic coordination meetings. The SAI designated as global lead for networking will call for the periodic meetings outside of the SC meetings. Each regional focal point is encouraged to develop a stakeholder list for the region.

| Table 1: Global and regional focal points |  |
| --- | --- |
| Global coordination networking | Brazil, US or Norway |
| ASOSAI | Indonesia or India? |
| CAROSAI | Tbc |
| EUROSAI | Norway |
| AFROSAI | Uganda |
| OLACEFS | Brazil |
| PASAI | Fiji |
| ARABOSAI | Iraq? |

| Table 1: Activity 4 Networking |  |  |  |
| --- | --- | --- | --- |
| Activities | Output | Target | Responsible SAI |
| - Cooperate with INTOSAI Regions | - WGEI activities included within the workplans of the INTOSAI regions - Collaborative activities undertaken with INTOSAI regions | Interact with each INTOSAI region at least once every 3 years | - Secretariat - Regional Representatives on the Steering Committee |
| - Engage INTOSAI bodies (for example: Governing board, General Secretariat, IDI, Goal Chairs, Working Groups, Task forces, WGEA, CBC, etc) | - Participate in activities and events of INTOSAI bodies - Identify areas of cooperation between WGEI and INTOSAI bodies | Participate in 2 activities or events of INTOSAI bodies every year | - Secretariat - Steering Committee |
| - Key External Stakeholder (external to the SAI community) networking and outreach based on the WGEI Stakeholder Strategy | - Continuous dialogue and follow-up with key External Stakeholders - Identify areas of cooperation between WGEI and External Stakeholders - Participate in relevant External Stakeholder activities | As required, see calendar of events | - Norway - Brazil - IDI - USA |
| - Engage academia and research organisations in WGEI activities | Academia and research organisations actively engaged in WGEI activities | 1 academic institution or research organisation actively engaged | - Norway - USA - Indonesia - AFROSAI-E |

- Mapping the different stakeholders and stakeholder groups

The table below provides an overview of the main stakeholders for the Working Group. The table includes how the stakeholders represent opportunities for WGEI and lists specific strategies for each stakeholder group.

| Table 2: An overview of stakeholders |  |  |  |
| --- | --- | --- | --- |
| Stakeholder | Description | Opportunity for WGEI | WGEI Strategy |
| INTOSAI bodies |  |  |  |
| WGEI members | WGEI’s main target group is its members and Supreme Audit Institutions in general. In the INTOSAI Strategic Goal on Knowledge Sharing, WGEI plays an important role in facilitating knowledge and experience sharing in the audit of extractive industries. | - Each member has unique experiences and resources to share | - Engage WGEI members in taking part in and implementing the activities in the WGEI Work Plan - Promote WGEI products to the WGEI members - Regional focal points should take the lead. - Encourage more SAIs to become members of WGEI - Facilitate information sharing between WGEI members |
| INTOSAI Regional Organizations | The INTOSAI Regional Organizations are autonomous entities, established for the purpose of promoting the professional and technical cooperation of its members on a regional basis. WGEI plays a role in coordinating with INTOSAI regional organizations in areas that deal with extractive industries audits. | - Existing platforms for knowledge sharing - Developed manuals and guidelines | - Request regional organizations to promote WGEI activities and products within their platforms - Encourage regional bodies to share their developed resources - Regional leads to liaise with respective INTOSAI regional body |
| INTOSAI Development Initiative (IDI) | IDI is an INTOSAI body that supports capacity building for SAIs in developing countries. In this way, IDI and WGEI share a common goal in contributing to improving SAIs’ capacity and knowledge in conducting audits. As an observer member, IDI should be involved and engaged in the WGEI activities. | - IDI has a unique insight and overview of the SAI community - IDI’s existing framework of programs and e-learning represents an opportunity to disseminate WGEI products and resources | - Involving IDI to promote WGEI activities and products - Use the INTOSAI-Donor Cooperation Tier 1 modality to solicit funds, administered by the IDI |
| NGOs, global initiatives on EI and Academia |  |  |  |
| Extractive Industries Transparency Initiative (EITI) | The EITI is the global standard to promote the open and accountable management of extractive resources. It is a platform where companies, government and CSOs work together in increasing transparency across the EI value chain. EITI has a great interest in the work of SAIs. | - EITI develops reports and information about the EI sector in various countries - EITI is increasingly interested in the work of SAIs | - Continuous dialogue with the EITI secretariat on how to involve SAIs in the EITI process and how SAIs can use EITIs work in their audits. - Invite EITI to WGEI events - Attend EITI events to promote the role of SAIs in auditing EI - Global approach: EITI: NAO Norway, Academia: GAO - Regional approach: EITI multi stakeholder group by member country or regional fp?. Regional universities |
| Other NGOs, for example: Natural Resource Governance Institute (NRGI), Publish What You Pay (PWYP), Oxfam, ATAF etc. IGF, IISD, | Several NGOs in the EI sector aim to promote better management of EI resources, and hence can be involved in WGEI activities. For example: NRGI has participated in a number of WGEI events. PWYP took part in the 2015 WGEI meeting, while ATAF has not been actively involved yet, but is a potential partner. | - NGOs have subject matter knowledge and experts that can be utilized - NGOs undertake a lot of research in the EI sector that highlights specific risks | - Invite NGO representatives to WGEI events - Invite NGOs to contribute to the WGEI newsletter - Partner with NGOs to solicit funding for WGEI activities - Use NGO subject matter experts as facilitators in WGEI trainings - Discuss joint WGEI-NGO training activities - Global approach: NRGI: NAO Norway. ATAF: OAG Uganda. IGF: NAO Norway - Regional approach: |
| Development agencies |  |  |  |
| World Bank (EI unit and EGPS, based in Washington DC), International Monetary Fund (IMF), UNDP, UNODC, EU, German Corporation for International Cooperation- GmBH (GIZ), DFID, country development agencies (Norway, Netherlands etc.) | Many of these agencies run specific programs on strengthening the management of the EI sector. These include UNDP and GIZ. For example: GIZ supported WGEI activities in its first year of operation. World Bank is the host of the GOXI platform. WGEI submitted a funding proposal to DFID in 2017. | - The EI sector is a high priority area for many development agencies - The majority of WGEI members fall within the scope and interest of these agencies | - Partner with development agencies to deliver training and capacity building support - Create synergies with existing initiatives - Global approach: WB, UNDP and IMF: GAO. EU, GIZ, DFID: NAO Norway - Regional approach: ADB, AfDB, other regional development banks. |
| EI Companies |  |  |  |
| Extractive industries companies and organizations | These include companies that are involved in the extraction or production of mineral and petroleum resources. Some of these companies operate worldwide. They are also organized in special interest organizations that promote their interests. | EI companies have an interest in a transparent, well-managed EI sector. It is likely that they would prefer a strong and competent SAI community which works towards more accountability, rule of law and stability. | - Attend conferences to learn more about the “business perspective” and relevant risks - Invite the industry to WGEI events to get different perspectives |

- Plan of events for stakeholder engagement and outreach 2025 - 2027

| Table 3: Events |  |  |
| --- | --- | --- |
| 2025 |  |  |
| Period | Event/Activity | Stakeholder(s) |
| 3-6 February | Mining Indaba in Cape Town | Mining companies and governments |
|  | KSC Meeting | KSC |
| November | IGF annual general meeting | IISD, IGF, donors, NGOs, Academia |
| July | AFROSAI-E Technical Update | AFROSAI-E |
| October | INCOSAI Meeting | INTOSAI, SAIs and other INTOSAI bodies |
| 2026 |  |  |
| Period | Event/Activity | Stakeholder(s) |
| February | Mining Indaba in Cape Town | Mining companies and governments |
| Tbc | KSC Meeting | KSC |
| July | AFROSAI-E Technical Update | AFROSAI-E |
| Tbc | WGEI All Members’ meeting | WGEI members, INTOSAI bodies and key stakeholders |
| Tbc | EITI global conference | EITI and other stakeholders |
| November | IGF annual general meeting | IISD, IGF, donors, NGOs, Academia |
| 2027 |  |  |
| Period | Event/Activity | Stakeholder(s) |
| February | Mining Indaba in Cape Town | Mining companies and governments |
| Tbc | KSC Meeting | KSC |
| November | IGF annual general meeting | IISD, IGF, donors, NGOs, Academia |
| Tbc | AFROSAI-E Technical Update | AFROSAI-E |

A stakeholder in this context is an organization, institution or a party that has or may have an interest in WGEIs activities, and can either affect or be affected by the activities of WGEI.