## Slide 1: Activity 3: Knowledge and experience sharing Performance Report (2023 – 2025)
Presented by SAIs Brazil, Norway and United States
At WGEI All Members’ Meeting
16th – 19th June 2026 Brasilia, Brazil

## Slide 2
Target
1 academic institution or research organisation actively engaged
Output
Academia and research organisations actively engaged in WGEI activities
Achievements
Reached out to three reasearch/academic organisations to provide webinar on extactive industry related topics (overlap with Activity 2.0 i):
  April 2025 – Soverign Wealth Funds: Corruptions and Other Governance Risks, Lakshmi Kumar, Ajdunct Professor at Georgetown University
  July 2025 – Seafloor Mining: Regulatory Quagmire or Key to Energy Transition, Dr. Seaver Wang, Breakthrough Institute
  April 2026 – The promise of Byproduct Recovery to Meet Critical Mineral Needs, Dr. Elizabeth Holley, Colorado School of Mines
4.i.d Academia and research organisations

## Slide 3
Target
Develop and implement a process for refreshing and updating the list of audit reports on the WGEI website
Output
Developed options for collecting and making available EI reports
Achievements
Examined audit report databases maintained by other INTOSAI working groups
Met with representatives of WGEA and discussed the logistics and procedures behind their audit report database
The Secretariat successfully deployed a new WGEI website with a new database feature
Working on drafting Standard Operating Procedure for updating the audit databases tailored to the needs of WGEI Secretariate and WGEI members
Working on preliminary IT Tool (Microsoft Forms Survey) to send out to WGEI members regarding EI Audit Reports
3.0 i – Collect and Prepare EI Audit Reports for Upload to Websites

## Slide 4
Target
Update and refresh the EI Auditors Toolkit
Output
EI Toolkit in new format
Achievements
Converted existing toolkit to PDF format containing the same graphical user interface.
GAO requested feedback in 2025 from WGEI members on EI Auditors Toolkit and made revisions as appropriate
GAO conducted a thorough review of the material in the EI Auditors Toolkit, revised outdated sections, updated links to external organizations and documents
Prepared toolkit in English, Spanish, French, and Arabic
Secretariat will share with Steering Committee members for review and incorporate and remaining comments
3.0 vi. – Manage and Update the EI Auditors Toolkit